ERNEST & JOHNNIE WHITE RECOVERY HOUSE, L.L.C. PROFESSIONAL SERVICES AGREEMENT Recovery Program Development, Operations & Technical Assistance · Version 4.0 · 2026

This Agreement in Context This Professional Services Agreement is Agreement 2 of 3 in the Ernest & Johnnie White Recovery House operational structure. Agreement 1: W & W Properties (Landlord) leases 1414 12th Street to Ernest & Johnnie White Recovery House, L.L.C. (Tenant) Agreement 2 (this document): Ernest & Johnnie White Recovery House, L.L.C. contracts Grace For Addictions as program operator Agreement 3: Entity Structure & NARR Compliance Disclosure — submitted with NARR certification application All three agreements must be executed before operations commence.

PARTIES

| OPERATOR / CLIENT Ernest & Johnnie White Recovery House, L.L.C. Iowa Business No. 872192 1414 12th Street, Des Moines, Iowa 50314 Sole Member: Curtis White Property leased from W & W Properties Hereinafter: "Operator" Founding Sponsor / Authorized Representative: Curtis White 515-208-1151 ejwrh@rcoiowa.org | PROGRAM OPERATOR / SERVICE PROVIDER Grace For Addictions 501(c)(3) Recovery Community Organization President: Dave Stout Executive Director: Creates initial documents, NARR certification, compliance, and renewal Hereinafter: "Service Provider" President / Authorized Signatory: Dave Stout, President GFA Office: 515-220-8771 Residents Warmline: 515-310-DIAL (3425) or Toll Free +1 (877) 295-2535 |
| --- | --- |

Structural Framework Grace For Addictions serves as contracted program operator, not as co-owner, co-operator, or partner of Operator. Operator retains sole responsibility for housing, property, and financial management. Service Provider holds operational authority over all program functions. This distinction is required for NARR certification, Fair Housing Act compliance, Iowa Code § 562A.5 protections, and clean liability separation between entities. Note on Signing Authority: Dave Stout signs as President of Grace For Addictions. Executive Director manages day-to-day program services and works directly with the House Manager. If the Executive Director position changes, this Agreement remains in force — the role is defined by function, not by the individual holding it.

Article 1 — Relationship of the Parties

1.1  Independent Contractor Status

Service Provider is an independent contractor. Service Provider is not an employee, partner, joint venturer, co-owner, or co-operator of Operator, Ernest & Johnnie White Recovery House, L.L.C., or W & W Properties.

1.2  Operator Role — Property Operator & Founding Sponsor

Operator (Ernest & Johnnie White Recovery House, L.L.C.) is the recovery house operator, leasing the property from W & W Properties. Curtis White is the founding sponsor whose vision and property provision make this program possible. Operator retains sole authority over housing operations, property lease obligations, financial management of program fees, and property compliance.

1.3  Service Provider Role — Program Operator

Grace For Addictions is the documented program operator. Service Provider’s name appears on NARR certification materials, participant agreements, program policies, and regulatory filings. The Executive Director: Creates initial program documents, leads NARR certification, NARR compliance, and NARR renewal. Recovery Navigators, Peer Recovery Coaches, and Volunteers deliver, facilitate, coordinate, and support program services. This role is defined functionally and is not tied to any individual by name in this Agreement.

1.4  No Personal Guarantee

Dave Stout signs as President of Grace For Addictions, overseeing all day-to-day programs, services, and operations. Curtis White signs solely as Sole Member of Ernest & Johnnie White Recovery House, L.L.C. Neither party is personally financially liable for the other’s obligations.

1.5  Nonprofit Integrity

All services are consistent with Grace For Addictions’ 501(c)(3) charitable mission, represent fair market value, and constitute an arms-length professional services arrangement.

Article 2 — Scope of Services

PHASE 1 · PROGRAM BUILD-OUT & LAUNCH · Milestone Fees

2.1.A  Complete Operational System

- Men’s Resident Handbook — trauma-informed, reentry-aware, NARR-aligned

- Staff Operations Manual — intake, drug testing, incident response, documentation

- All participant forms including Intake Application, IRP, Drug Screen Log, Grievance Form

- House Rules, Phase Structure (1/2/3), Curfew Framework, Return-to-Use Response

2.1.B  Legal Documentation

- Participant Agreement (program participation, not a lease)

- Legal Authority for Emergency Removal (Iowa Code §§ 562A.5, 562A.27A, Iowa Admin. Code § 481-65.16(5))

2.1.C  NARR Level II Readiness

- Full NARR Standard 3.0 compliance crosswalk and self-assessment

- Site readiness checklist and certification application support

2.1.D  VRCC Digital Platform

- Virtual Recovery Community Center configuration, resident portal, staff portal, intake module, bed management

2.1.E  Staff Training

- House Manager and peer mentor orientation

- Naloxone/Narcan training

- Drug testing protocol and documentation standards

PHASE 2 · ONGOING PROGRAM OPERATIONS · Monthly Retainer

2.2.A  Program Oversight

- Executive Director: Creates initial program documents, NARR certification, compliance, and renewal

- NARR Level II compliance monitoring and annual renewal support

- Iowa HHS reporting compliance guidance

2.2.B  Recovery & Reentry Support

- Recovery coaching via credentialed peer coaches

- Individual Recovery Plan development and coordination

- Reentry-informed case coordination — employment, benefits, legal navigation

- Crisis response and 24/7 on-call program coverage

2.2.C  Wrap-Around Services

- Transportation coordination — recovery meetings, medical appointments, employment

- Alumni support and GFA recovery community network connection

2.2.D  Referral Pipeline Support

- Program marketing materials and referral distribution content

- Referral relationship development — courts, probation, reentry programs, treatment providers (formal referral agreements executed by Operator)

- VRCC intake portal management and intake screening support

Article 3 — Operator’s Responsibilities

- Maintain the Premises per the W & W Properties Lease Agreement

- Provide furnishings for all 10 resident beds

- Collect resident program fees per the tiered schedule below and maintain financial records: • Shared room: $175/week or $660/month • Single private room: $200/week or $760/month • Grandfathered participant (Bradley): $150/week — existing rate honored

- Pay all property-related expenses: rent to W & W Properties, all utilities (water, electric, gas/heat, trash, internet), and property insurance

- Carry premises liability insurance naming Service Provider as additional insured

- Pay Service Provider’s invoices within 10 business days of receipt

- Not interfere with program operations, intake, discharge, or any program function

- Develop and introduce reentry referral relationships to Service Provider (formal agreements executed by Service Provider as program operator)

Article 4 — Compensation

| Deliverable / Service | Fee | When |
| --- | --- | --- |
| Complete Operational System | $1,500 | On delivery |
| Participant Agreement + Legal Authority docs | $500 | On delivery |
| NARR Level II readiness package | $1,000 | On delivery |
| VRCC digital platform setup | $750 | On go-live |
| Staff training | $750 | On completion |
| PHASE 1 TOTAL | $4,500 | One-time |
| Ongoing program management & services | $1,200/month | 1st of each month |
| Annual NARR renewal support | $500/year | At renewal |

Fair Market Value Basis Actual market evidence at 1414 12th Street supports the following fee structure: • Shared room: $175/week or $660/month • Single private room: $200/week or $760/month • Grandfathered participant (Bradley): $150/week — existing rate honored At $175/week average with 10 beds and 70% occupancy (6 residents), monthly gross program revenue is approximately $5,317. The $1,200/month retainer represents approximately 22.6% of gross revenue at 70% occupancy, and approximately 17% at full occupancy. This is fair market value for defined professional services. All utilities are Operator’s responsibility and are incorporated into participant program fees.

4.1  Phase 1 Startup Fee — Three-Installment Payment Plan

The Phase 1 startup fee of $4,500 is payable in three equal installments of $1,500 each, subject to the following conditions:

- The monthly fee identified in detail in paragraph 4.1(b) will begin immediately regardless of whether the phase 1 payments of $1,500 have reached the minimum occupancy required for said payments to begin.   The sum to be paid will be based on the chart in paragraph 4.1(b).  The fee paid will be based on occupancy but as long as there is at least one occupant the fee will be paid beginning in the first month based on the chart in paragraph 4.1(b)

- Phase 1 startup installments are triggered only once occupancy reaches 70% — 7 of 10 beds    occupied.

- Once the 70% threshold is met: $1,500 invoiced in Month 1 of threshold, $1,500 in Month 2, and $1,500 in Month 3.

- If occupancy falls below 70% between installments, the next installment is deferred until 70% occupancy is maintained for 30 consecutive days.

- Earned milestone fees are non-refundable once the corresponding deliverable is substantially completed.

Example: If first intake occurs in Month 1 and 70% occupancy is first reached in Month 3, startup installments are invoiced in Month 3, 4 and 5. The monthly fee identified in paragraph 4.1(b) begins in Month 1 even if the startup fee has not yet been invoiced become occupancy is below 70%.

.

4.1(b) Occupancy-  Based Monthly Retainer Adjustment

The $1,200/month retainer set forth in Article 4 is based on 70% occupancy (6 or more residents in a 10-bed house). The retainer is tied to actual program fee revenue collected by Operator. If occupancy falls below 70%, the monthly retainer shall be adjusted as follows:

| Number of Residents / Participants | Monthly Service Fee |
| --- | --- |
| 6 or more (70%+ occupancy) | $1,200 |
| 5 | $1,000 |
| 4 | $800 |
| 3 | $600 |
| 2 | $400 |
| 1 | $200 |
| 0 | $0 |

The adjusted monthly fee shall be calculated based on the number of residents actively paying program fees as of the first day of the billing month. Operator shall provide Service Provider with a resident count on the first business day of each month. The $1,200/month retainer is restored immediately upon return to 6 or more paying residents.

4.2  Grandfathered Participant Rate — Bradley

Bradley’s existing rate of $150 per week is grandfathered and shall remain in effect for the duration of his continuous residency. This grandfathered rate does not apply to any other participant and does not set a precedent for future fee negotiations.

4.3  Monthly Retainer — Invoice and Payment

Service Provider invoices Operator on the first business day of each month for the prior month’s retainer. Operator pays within 10 business days. If 30 or more days past due, Service Provider may suspend ongoing services with written notice until payment is received.

4.4  Program Fee Ownership

All resident program fees are collected by and belong to Operator. Service Provider has no claim to program fees beyond the monthly retainer. Service Provider does not handle, hold, or manage Operator’s program fee accounts.

4.5  Annual Rate Review

The monthly retainer and program fee schedule are reviewed annually at Agreement renewal. Either party may propose adjustments with 60 days’ written notice. Any change requires a written amendment signed by both parties.

Articles 5–9 — Insurance, Term, Confidentiality, Disputes, General

5. Insurance & Liability

Service Provider carries: CGL ($1M/$2M), Professional Liability ($1M), Workers’ Compensation. Operator named as additional insured on CGL. Operator carries premises liability ($1M minimum). Service Provider named as additional insured. Limitation of liability: Service Provider’s liability capped at fees paid in prior 12 months. Mutual indemnification for each party’s own acts.

6. Term & Termination

Initial term: 12 months, auto-renews annually. Termination for cause: 30 days’ notice with cure period. Termination without cause: 60 days’ notice. On termination: all program documentation delivered to Operator; outstanding invoices due immediately; earned milestone fees non-refundable.

7. Confidentiality

All participant information protected under 42 CFR Part 2, HIPAA, and Iowa law. No disclosure without legal requirement or written participant consent. Survives termination.

8. Dispute Resolution

Good-faith negotiation → non-binding mediation in Polk County, Iowa → binding AAA arbitration in Des Moines. Iowa law governs. Prevailing party recovers reasonable attorney’s fees.

9. General

- Entire agreement — supersedes all prior discussions; amendments in writing signed by both parties

- Severability — unenforceable provisions severed; remainder in full force

- No personal guarantee — Dave Stout signs as President only; Curtis White signs as Sole Member only

- Attorney review encouraged — both parties confirm opportunity to seek Iowa legal counsel

- Governing law — State of Iowa

Article 10 — Signatures

By signing, each party confirms Full review of this Agreement, opportunity to seek legal counsel, and voluntary agreement to be bound by its terms.

OPERATOR — ERNEST & JOHNNIE WHITE RECOVERY HOUSE, L.L.C.

| Curtis White, Sole Member — Ernest & Johnnie White Recovery House, L.L.C. | Date |
| --- | --- |

| Title: Founding Sponsor / Owner | Iowa Business No. 872192 |
| --- | --- |

PROGRAM OPERATOR — GRACE FOR ADDICTIONS

| Dave Stout, President — Grace For Addictions | Date |
| --- | --- |

| Grace For Addictions · 501(c)(3) Recovery Community Organization | GFA Office: 515-220-8771 · ejwrh@rcoiowa.org · Residents Warmline: 515-310-DIAL (3425) or Toll Free +1 (877) 295-2535 |
| --- | --- |

Ernest & Johnnie White Recovery House, L.L.C.  ·  Professional Services Agreement v4.0  ·  2026  ·  Confidential